## 12 pm class
Developing your personal website
What do we need? Domain name, interface, hosting company, coding, team (1 person to do troubleshooting and to integrate it with another platform; 1 person for SEO; 1 person to design the aesthetics), design, tool to make the website, e.g. Wix
WBS Items | # Units/Hrs | Cost/unit/hour | Subtotals | WBS Level 2 totals | % of totals
SEO |  |  |  | 470
PM | 7 | 50 | 350
SEO person | 4 | 30 | 120
design
PM | 40 | 50 | 2000 | 3600
Design person | 40 | 40 | 1600
Coding
PM | 45 | 50 | 2250 | 2460
Troubleshooting / integration person | 7 | 30 | 210
Domain name |  |  | 20 | 20
Hosting |  |  | 80 | 80
Subtotal |  |  | 6630
Contingency Reserves 10% |  |  | 663
Total project cost estimate |  |  | 7293

## 8 am class
Developing your personal website
what we need: banner image, business name (do we need to register a business?), logo, content, business location for registrations purposes), time, rules, team (you: coding; Friend 1 - design part; Friend 2 - business ideas (he's business savvy)
WBS Items | # Units/Hrs | Cost/unit/hour | Subtotals | WBS Level 2 totals | % of totals
business setup |  |  |  | 305
PM | 7 | 35 | 245
Friend 2 | 3 | 20 | 60
Interface design |  |  | 0
PM | 40 | 35 | 1400 | 2200
Friend 1 | 40 | 20 | 800
Web development
PM | 65 | 35 | 2275 | 2755
Friend 1 | 24 | 20 | 480
Domain name |  | 20 | 20 | 20
Hosting |  | 80 | 80 | 80
Subtotal |  |  | 5360
Reserves 15% |  |  | 804
Total project cost estimate |  |  | 6164