## Sheet1
12-month project = projected duration of 12 months
PV = $30,000 | 30000 | Formulas
EV = $20,000 | 20000 | EV = PV of all completed work
AC = $28,000 | 28000 | CV = EV-AC | CV | -8000
BAC (budget at completion = planned budget) = $130,000 | 130000 | SV = EV-PV | SV | -10000
|  | CPI = EV/AC | CPI | 71.43%
Calculate the values for: |  | SPI = EV/PV | SPI | 66.67%
CV (cost variance) |  | EAC = BAC/CPI | EAC | 182000
SV (schedule variance) |  | ETC = projected/original duration of project/SPI | ETC | 18
CPI (cost performance index)
SPI (schedule performance index) If SPI =1, project is on track; SPI > 1, project is doing better than planned, meaning ahead of schedule; if SPI < 1, project is doing worse than planned meaning behind schedule
EAC (estimate at completion = revised total budget based on where we are today in $$)
ETC (estimated time to complete = revised duration of the project based on where you are today in months or days or years)
Is the project ahead or behind of schedule, and why? |  |  |  | behind schedule because SV is negative
Is the project under or over budget, and why? |  |  |  | over budget because CV is negative
Is the project performing better or worse than planned, and why? |  |  |  | worse because CPI and SPI are below 1
How long will it take to finish the project in months? Justify your answer. |  |  |  | 18 months
What will be the resulting project cost based on where we are now? Justify your answer. |  |  |  | 182000

## Sheet1 (2)
12-month project = projected duration of 12 months
PV = $30,000 | 30000 | Formulas
EV = $20,000 | 40000 | EV = PV of all completed work
AC = $28,000 | 28000 | CV = EV-AC | CV | 12000
BAC (budget at completion = planned budget) = $130,000 | 130000 | SV = EV-PV | SV | 10000
|  | CPI = EV/AC | CPI | 142.9%
Calculate the values for: |  | SPI = EV/PV | SPI | 133.3%
CV (cost variance) |  | EAC = BAC/CPI | EAC | 91000
SV (schedule variance) |  | ETC = projected/original duration of project/SPI | ETC | 9
CPI (cost performance index)
SPI (schedule performance index) If SPI =1, project is on track; SPI > 1, project is doing better than planned, meaning ahead of schedule; if SPI < 1, project is doing worse than planned meaning behind schedule
EAC (estimate at completion = revised total budget based on where we are today in $$)
ETC (estimated time to complete = revised duration of the project based on where you are today in months or days or years)
Is the project ahead or behind of schedule, and why? |  |  |  | ahead of schedule because SV is positive
Is the project under or over budget, and why? |  |  |  | under budget because CV is positive
Is the project performing better or worse than planned, and why? |  |  |  | better because CPI and SPI are above 1
How long will it take to finish the project in months? Justify your answer. |  |  |  | 9 months
What will be the resulting project cost based on where we are now? Justify your answer. |  |  |  | 91000